## 1.Cover
FFT_AXI_stream VERIFICATION CHECKLIST
| Revision | : Rev0.1
| Prj Duration | : 08/10/2026 - /2026
| Author | : Hungpv79
| Approval | : Nhannh18

## 2.History_ver
HISTORY
Description
- The history is used for recording all modification of this document
- Please update exactly info to review correctly in the future
No | Date | Content | Updated by | Revision | Remark
1 | 2026-08-10 | - Create new | Hungpv79 | R0.1

## 3.Summary
SUMMARY REPORT
Description
- This sheet is used to collect and summarize all
results from other sub sheets
Summary Result
Status | Level | Revision | ENV revision | No. of planned items | No. of finished items | Remain | Remark
Done | RTL |  |  | 9 | 9 | 0
On Going | Pre-simulation |  |  | 0 | 0 | 0
Not yet | Post-simulation |  |  | 0 | 0 | 0
Note on C10: - Refer to Sheet 6.Testlist for detail
Note on D10: - Testbench revision, hash of ENV on repo

## 4.Definition_list
DEFINITION LIST
Table D_1-1: Numeral
Prefix | Definition | Remarks
'h/h' | Hex numeral | Ex: 'hFF
'b/b' | Binary numeral | Ex: 'b1111_1111
None | Decimal | Ex: 255
Table D_1-2: Abbreviation
Abbreviation | Definition | Remarks
H | High Level
L | Low level
ALL-H | All bits are set to high
ALL-L | All bits are set to low
Pol | Polarity
Addr | Address
REG | Register
TM | Test-scenario
FCOV | Functional Coverage
ID | Identifier
Fund.ID | Fundamental ID
Table D_1-3: Priority
Classification | Definition | Remarks
High | Items to be done up to 1st release of source code
Normal | Items to be done up to source code Fix
Low | Items up to T.O

## 5.Function_list MD (hidden)
TESTPLAN
Classification 1 | Classification 2 | Classification 3 | Classification 4 | Classification 5 | Classification 6 | Cover type | Reference section in specification | Note
1. Operation
| 1. FFT | [5 empty] | 1. Mô tả tính năng: Tham số cấu hình
|  | 1. N:16384 |  |  |  |  | 4.2. CONFIG: NFFT | output frame maybe overlap because If cyclic prefix insertion is used, more samples are unloaded from the core than are loaded.
|  |  | 1. full stage |  |  |  | 4.2. CONFIG: CP_LEN
|  |  | 2. change configuration for each frame at the end of previous frame operation |  |  |  | 6.2. Chi tiết Configure Sequence cho FFT theo AXI Stream Interface --> Step 5: Lặp lại xử lý (Processing loop)
|  |  |  | 1. less than full stage |  |  | 4.2. CONFIG: SCALE_SCH
2. cyclic prefix length and ouput frame due to inserting cyclic prefix
|  |  |  | 3. scale schedule |  |  | 6.2. Chi tiết Configure Sequence cho FFT theo AXI Stream Interface --> Step 4: Nhận dữ liệu đầu ra (Output data phase)
1. without overflow
2. with overflow
3. output frame overlap due to receiver is not ready
1. full stage with different N
2. less than full stage
|  |  | 4. Accuracy |  |  |  | 4. So sánh kết quả phần cứng với phần mềm bằng RMSE hoặc SNR
|  |  |  | 1. INPUT_W: 32 |  |  | 4. So sánh kết quả phần cứng với phần mềm bằng RMSE hoặc SNR
|  |  |  | 2. INPUT_W: 16 |  |  | 4. So sánh kết quả phần cứng với phần mềm bằng RMSE hoặc SNR
|  |  |  | 3. INPUT_W: 8 |  |  | 4. So sánh kết quả phần cứng với phần mềm bằng RMSE hoặc SNR
2. N:8192
3. N:4096
4. N:2048
5. N:1024
6. N:512
7. N:256
8. N:128
9. N:64
10. N:32
11. N:16
12. N:8
| 2. iFFT | [5 empty] | 1. Mô tả tính năng: Tham số cấu hình
|  | 1. N:16384 |  |  |  |  | 4.2. CONFIG: NFFT
|  |  | 1. full stage |  |  |  | 4.2. CONFIG: CP_LEN
|  |  | 2. change configuration for each frame at the end of previous frame operation |  |  |  | 6.2. Chi tiết Configure Sequence cho FFT theo AXI Stream Interface --> Step 5: Lặp lại xử lý (Processing loop)
|  |  |  | 1. less than full stage |  |  | 4.2. CONFIG: SCALE_SCH
2. cyclic prefix length and ouput frame due to inserting cyclic prefix
|  |  |  | 3. scale schedule |  |  | 6.2. Chi tiết Configure Sequence cho FFT theo AXI Stream Interface --> Step 4: Nhận dữ liệu đầu ra (Output data phase)
3. output frame overlap due to receiver is not ready
1. full stage with different N
2. less than full stage
|  |  | 4. Accuracy |  |  |  | 4. So sánh kết quả phần cứng với phần mềm bằng RMSE hoặc SNR
|  |  |  | 1. INPUT_W: 32 |  |  | 4. So sánh kết quả phần cứng với phần mềm bằng RMSE hoặc SNR
|  |  |  | 2. INPUT_W: 16 |  |  | 4. So sánh kết quả phần cứng với phần mềm bằng RMSE hoặc SNR | output frame maybe overlap because If cyclic prefix insertion is used, more samples are unloaded from the core than are loaded.
|  |  |  | 3. INPUT_W: 8 |  |  | 4. So sánh kết quả phần cứng với phần mềm bằng RMSE hoặc SNR
2. N:8192
3. N:4096
4. N:2048
5. N:1024
6. N:512
7. N:256
8. N:128
9. N:64
10. N:32
11. N:16
12. N:8
| 3. output cycle | [5 empty] | 1. Mô tả tính năng: Thời gian thực thi
| 4. channel status timing | [5 empty] | 6.2. Chi tiết Configure Sequence cho FFT theo AXI Stream Interface --> Step 4: Nhận dữ liệu đầu ra (Output data phase)--> 3. Tín hiệu đi kèm
2. reset | [7 empty] | due to no register default value check, so we need this scenario to confirm the IP reset
1. reset during operation

## 5.Function_list (2)
TESTPLAN
Classification 1 | Classification 2 | Classification 3 | Classification 4 | Cover type | Reference section in specification | Note
1. Reset (rstn and rstn_250Mhz) |  |  |  | Assertion | Clock và Reset
| 1. Reset on the fly: +) Reset when synchronization operation (acquisition) +) Reset when tracking occur +) Reset when interrupt occur +) Reset when tracking error occur +) Reset when caculating time +) Reset when streaming data out |  |  | Cover property
2. Software reset (only reset core) |  |  |  |  | Software reset
1. Reset on the fly: +) Reset when synchronization operation (acquisition) +) Reset when tracking occur +) Reset when interrupt occur +) Reset when tracking error occur +) Reset when caculating time +) Reset when streaming data out
| 2. SYNC_RESET field: +) reset when EN field is 0, and no reset when EN field not 0 |  |  | Covergroup, Cross
3. AXI4-Full |  |  |  |  | AXI4 Slave (miền clk) Bản đồ thanh ghi (Register Map)
| 1. Handshake |  |  | Protocol checker (VIP) |  | This scenario is verified in read/write register test.
| 2. Single-beat |  |  | Covergroup, Cross |  | This scenario is verified in read/write register test.
| 3. INCR burst |  |  | Covergroup, Cross |  | This scenario is verified in read/write register test.
| 4. WRAP burst |  |  | Covergroup, Cross |  | This scenario is verified in read/write register test.
| 5. WSTRB |  |  | Covergroup, Cross |  | This scenario is verified in read/write register test.
| 6. xRESP |  |  | Covergroup, Cross |  | This scenario is verified in read/write register test.
4. Register |  |  |  |  | Bản đồ thanh ghi (Register Map)
1. Reset value
2. Read-write access
3. Unaligned address
4. Alias offset
5. Reserved address
5. Synchronous behavior |  |  |  |  | Quá trình đồng bộ (hành vi phần cứng)
1. Disabled when EN not active
| 2. Interrupt mode |  |  |  | Xử lý ngắt
1. interrupt set by (VLD && VLDE) ¦¦ (ERR && ERRE)
2. interrupt_clear (highest priority)
| 3. Polling mode (disable interrupt) |  |  |  | Chế độ polling
| 4. pos |  |  |  | Dữ liệu ra và trạng thái (miền clk_250_MHz)
| 5. pos_valid |  |  | Assertion | Dữ liệu ra và trạng thái (miền clk_250_MHz)
| 6. NMSE (check output data) |  |  |  | Dữ liệu ra và trạng thái (miền clk_250_MHz)
| 7. m_axis_tvalid low when: +) EN = 0 +) tracking_error occur +) software reset |  |  | Assertion | Dữ liệu ra và trạng thái (miền clk_250_MHz)
| 8. tracking_error |  |  | Assertion | Dữ liệu ra và trạng thái (miền clk_250_MHz)
6. Parameter (set default value as spec) |  |  |  |  | Tham số cấu hình (Parameters)
1. POS_WIDTH (16 to 32)
2. REG_FILE
3. MUL_DELAY (1 to 5)
4. VERSION
5. CLR_CYCLES (1 to 255)
6. FFO_PHA_WIDTH
7. FFO_N_ITER

## 5.Function_list
TESTPLAN
Classification 1 | Classification 2 | Classification 3 | Classification 4 | Cover type | Reference section in specification | Note
1. Reset |  |  |  | Assertion |  | due to no register default value check, so we need this scenario to confirm the IP reset
| 1. Reset during operation |  |  | Cover Property
2. AXI Stream Protocol
| 1. Master: default ready assert/no-assert |  |  | AXI VIP Coverage
3. Operation
| 1. N:16384 |  |  | Covergroup | 1. Mô tả tính năng: Tham số cấu hình
|  | 1. FFT |  | Covergroup, Cross | 4.2. CONFIG: IFFT
|  | 2. iFFT |  | Covergroup, Cross | 4.2. CONFIG: IFFT
|  | 3. NFFT |  | Covergroup, Cross | 4.2. CONFIG: NFFT | output frame maybe overlap because If cyclic prefix insertion is used, more samples are unloaded from the core than are loaded.
|  | 4. CP_LEN |  | Covergroup, Cross | 4.2. CONFIG: CP_LEN
|  | 5. SCALE_SCH |  | Covergroup, Cross | 4.2. CONFIG: SCALE_SCH
|  | 6. Change configuration for each frame at the end of previous frame operation |  | Covergroup, Cross | 6.2. Chi tiết Configure Sequence cho FFT theo AXI Stream Interface --> Step 5: Lặp lại xử lý (Processing loop)
|  | 7. Output frame overlap due to receiver is not ready |  | Covergroup, Cross | 6.2. Chi tiết Configure Sequence cho FFT theo AXI Stream Interface --> Step 4: Nhận dữ liệu đầu ra (Output data phase)
8. Accuracy
|  |  | 1. INPUT_W: 32 | Covergroup, Cross | 4. So sánh kết quả phần cứng với phần mềm bằng RMSE hoặc SNR
|  |  | 2. INPUT_W: 16 | Covergroup, Cross | 4. So sánh kết quả phần cứng với phần mềm bằng RMSE hoặc SNR
|  | 9. Overflow |  | Covergroup, Cross | 5.2 Status Format
| 2. N:8192 | The same with N:16384 | The same with N:16384
| 3. N:4096 | The same with N:16384 | The same with N:16384
| 4. N:2048 | The same with N:16384 | The same with N:16384
| 5. N:1024 | The same with N:16384 | The same with N:16384
| 6. N:512 | The same with N:16384 | The same with N:16384
| 7. N:256 | The same with N:16384 | The same with N:16384
| 8. N:128 | The same with N:16384 | The same with N:16384
| 9. N:64 | The same with N:16384 | The same with N:16384
| 10. N:32 | The same with N:16384 | The same with N:16384
| 11. N:16 | The same with N:16384 | The same with N:16384
| 12. N:8 | The same with N:16384 | The same with N:16384
| 13. Channel status timing |  |  | Assertion | 6.2. Chi tiết Configure Sequence cho FFT theo AXI Stream Interface --> Step 4: Nhận dữ liệu đầu ra (Output data phase)--> 3. Tín hiệu đi kèm
4. Performance
| 1. Output cycle |  |  | Test Result | 1. Mô tả tính năng: Thời gian thực thi | Verify at scoreboard

## 5.Function_list-old (hidden)
TESTPLAN
Classification 1 | Classification 2 | Classification 3 | Classification 4 | Reference section in specification | Note
EX: 1. Func 1 | Ex: 1. Func 1-1 | - | - | Section 1.1.1 in Design Specification
| Ex: 2. Func 1-2 | - | - | Section 1.1.2 in Design Specification
1. Operation | 1. FFT | 1. full stage with different N |  | 1. Mô tả tính năng: Tham số cấu hình
|  | 2. less than full stage |  | 4.2. CONFIG: NFFT
|  | 3. cyclic prefix length and ouput frame due to inserting cyclic prefix |  | 4.2. CONFIG: CP_LEN | output frame maybe overlap because If cyclic prefix insertion is used, more samples are unloaded from the core than are loaded.
|  | 4. scale schedule | 1. without overflow | 4.2. CONFIG: SCALE_SCH
2. with overflow
|  | 5. change configuration for each frame during operation |  | 6.2. Chi tiết Configure Sequence cho FFT theo AXI Stream Interface --> Step 5: Lặp lại xử lý (Processing loop)
|  | 6. output frame overlap due to receiver is not ready |  | 6.2. Chi tiết Configure Sequence cho FFT theo AXI Stream Interface --> Step 4: Nhận dữ liệu đầu ra (Output data phase)
7. Accuracy
| 2. iFFT | 1. full stage with different N |  | 1. Mô tả tính năng: Tham số cấu hình
|  | 2. less than full stage |  | 4.2. CONFIG: NFFT
|  | 3. cyclic prefix length and frame overlap due to inserting cyclic prefix |  | 4.2. CONFIG:CP_LEN | output frame maybe overlap because If cyclic prefix insertion is used, more samples are unloaded from the core than are loaded.
|  | 4. scale schedule | 1. without overflow | 4.2. CONFIG: SCALE_SCH
2. with overflow
|  | 5. change configuration for each frame during operation |  | 6.2. Chi tiết Configure Sequence cho FFT theo AXI Stream Interface --> Step 5: Lặp lại xử lý (Processing loop)
|  | 6. output frame overlap due to receiver is not ready |  | 6.2. Chi tiết Configure Sequence cho FFT theo AXI Stream Interface --> Step 4: Nhận dữ liệu đầu ra (Output data phase)
7. Accuracy
| 3. output cycle |  |  | 1. Mô tả tính năng: Thời gian thực thi
| 4. channel status timing |  |  | 6.2. Chi tiết Configure Sequence cho FFT theo AXI Stream Interface --> Step 4: Nhận dữ liệu đầu ra (Output data phase)--> 3. Tín hiệu đi kèm
2. reset | 1. reset during operation

## 6.Testlist
TESTLIST
[6 empty] | RTL |  |  |  | Pre-simulation |  |  |  | Post-simulation
Function |  | Confirm method |  | Priority | Scenario name | No. of planned items | No. of finished items | Started date | Finished date | No. of planned items | No. of finished items | Started date | Finished date | No. of planned items | No. of finished items | Started date | Finished date | In charge person | Note
Classification 1~4 | Fund. ID | What is checked | How to check | - | - | 9 | 9 | - | - | 19 | 10 | - | - | 19 | 19 | - | - | -
Classification 1: 1. Reset Classification 2: 1. Reset during operation | F1.1 | 1. OBJECTIVE: Verify operation of DUT when trigger reset during data processing and resume normal operation after reset release. 2. DETAILS: +) Apply asynchronous reset at (streaming data_in, computing data, and streaming data_out phase) . +) Config nfft = 3 (other field is default) and random data_in. +) Verify behavior of DUT after reset release. 3. PASS CRITERIA: No error. | Scoreboard + Assertion | High | tc_reset_on_the_fly_F1_1 | 1 | 1 | 2025-02-24 | 2025-02-26 | 1 | 1 | 2025-09-17 | 2025-09-19 | 1 | 1 | 2025-09-17 | 2025-09-19 | Hungpv79
Classification 1: 2. AXI Stream Protocol Classification 2: 1. Master: default ready assert/no-assert | F2.2 | 1. OBJECTIVE: Verify operation of the DUT when disable default_tready. 2. DETAILS: +) Random nfft, cp_len, ifft, and scale_sch. +) Random data_in (no overflow). +) Delay tready of data_out with last beat is large cycle and verify output result 3. PASS CRITERIA: No error | Scoreboard + Assertion | High | tc_fft_no_default_tready_F2_1 | 1 | 1 | 2025-03-25 | 2025-03-25 | 0 | 0 | 2025-09-17 | 2025-09-19 | 0 | 0 | 2025-09-17 | 2025-09-19 | Hungpv79
Classification 1: 3. Operation Classification 2: 1. N:16384 Classification 3: 1. FFT | F3.1.1 | 1. OBJECTIVE: Verify FFT function. 2. DETAILS: +) Configure register with FFT mode, (other field is default) (NP = 16384). +) Random data_in (no overflow) and verify output result 3. PASS CRITERIA: No error. | Scoreboard | Normal | tc_fft_fftSimple_F3_1_1 | 1 | 1 | 2025-11-19 | 2025-11-19 | 2 | 1 | 2025-09-17 | 2025-09-19 | 2 | 2 | 2025-09-17 | 2025-09-19 | Nhannh18
Classification 1: 3. Operation Classification 2: 1. N:16384 Classification 3: 2. iFFT | F3.1.2 | 1. OBJECTIVE: Verify IFFT function. 2. DETAILS: +) Configure register with IFFT mode, (other field is default) (NP = 16384). +) Random data_in (no overflow) and verify output result 3. PASS CRITERIA: No error. | Scoreboard | Normal | tc_fft_ifft_F3_1_2 | 1 | 1 | 2025-11-19 | 2025-11-19 | 2 | 1 | 2025-09-17 | 2025-09-19 | 2 | 2 | 2025-09-17 | 2025-09-19 | Nhannh18
Classification 1: 3. Operation Classification 2: 1. N:16384 Classification 3: 3. NFFT | F3.1.3 | 1. OBJECTIVE: Verify NFFT function (all supported value). 2. DETAILS: +) Configure register with all possible NFFT value (other field is default) and random data_in (no overflow) verify output result of DUT 3. PASS CRITERIA: No error | Scoreboard | Normal | tc_fft_nfft_F3_1_3 | 1 | 1 | 2025-11-18 | 2025-12-13 | 2 | 1 | 2025-09-17 | 2025-09-19 | 2 | 2 | 2025-09-17 | 2025-09-19 | Nhannh18
Classification 1: 3. Operation Classification 2: 1. N:16384 Classification 3: 4. CP_LEN | F3.1.4 | 1. OBJECTIVE: Verify CP_LEN function. 2. DETAILS: +) Configure register with all possible cp_len value with NFFT ((other field is default)) and random data_in (no overflow) +) Verify output result of DUT. 3. PASS CRITERIA: No error. | Scoreboard | Normal | tc_fft_cplen_F3_1_4 | 1 | 1 | 2025-11-30 | 2026-01-01 | 2 | 1 | 2025-09-17 | 2025-09-19 | 2 | 2 | 2025-09-17 | 2025-09-19 | Nhannh18
Classification 1: 3. Operation Classification 2: 1. N:16384 Classification 3: 5. SCALE_SCH | F3.1.5 | 1. OBJECTIVE: Verify SCALE_SCH function. 2. DETAILS: +) Configure register with all possible scale_sch value and nfft (other field is default). +) Random data_in (no overflow) and verify output result of DUT. 3. PASS CRITERIA: No error. | Scoreboard | Normal | tc_fft_scaleSch_F3_1_5 | 1 | 1 | 2025-01-02 | 2025-03-28 | 2 | 1 | 2025-09-17 | 2025-09-19 | 2 | 2 | 2025-09-17 | 2025-09-19 | Nhannh18
Classification 1: 3. Operation Classification 2: 1. N:16384 Classification 3: 6. Change configuration for each frame at the end of previous frame operation | F3.1.6 | 1. OBJECTIVE: Verify operation of DUT when change configuration for each frame at the end of previous frame operation 2. DETAILS: +) Verify frame completes with configuration A. +) Wait all data_out stream complete and verify result. +) Then verify next frame uses configuration B as above. 3. PASS CRITERIA: No error. | Scoreboard | Normal | N/A (Covered by other tests) | 0 | 0 | - | - | 2 | 1 | 2025-09-17 | 2025-09-19 | 2 | 2 | 2025-09-17 | 2025-09-19 | Nhannh18 | This scenario is verified implicitly in all other tests.
Classification 1: 3. Operation Classification 2: 1. N:16384 Classification 3: 7. Output frame overlap due to receiver is not ready | F3.1.7 | 1. OBJECTIVE: Verify configuration changes occur mid-operation. 2. DETAILS: +) Enable override test in config +) Set default_tready = 0 +) Send random config data +) Send random data_in (ensure no overflow) continously and set delay_tvalid for data_in. +) Verify which data_in is overrided (removed and not compare with model). +) Compare result of data_in not overrided with model 3. PASS CRITERIA: No error. | Scoreboard | Normal | tc_fft_override_frame_F3_1_7 | 1 | 1 | 2025-01-09 | 2025-09-17 | 2 | 1 | 2025-09-17 | 2025-09-19 | 2 | 2 | 2025-09-17 | 2025-09-19 | Nhannh18
Classification 1: 3. Operation Classification 2: 1. N:16384 Classification 3: 8. Accuracy | F3.1.8 | 1. OBJECTIVE: Verify accuracy of RMSE 2. DETAILS: +) Verify accuracy with different INPUT_W size and NFFT. +) Calculate the output results and tune the model such that the RMSE remains within the acceptable error range. 3. PASS CRITERIA: No error. | Scoreboard | High | N/A (Covered by other tests) | 0 | 0 | - | - | 2 | 1 | 2025-09-17 | 2025-09-19 | 2 | 2 | 2025-09-17 | 2025-09-19 | Nhannh18 | This scenario is verified implicitly in all other tests.
Classification 1: 2. Operation Classification 2: 1. N:16384 Classification 3: 9. Overflow | F3.1.9 | 1. OBJECTIVE: Verify overflow detection. 2. DETAILS: +) Enable overflow test in config +) Send random config data (nfft, ifft, and cp_len = 0) and set scale_sch. If this data_in overflowed, then send new config data with scale_sch larger than previous config data. +) Send random data_in +) Verify operation of overflow flag. 3. PASS CRITERIA: No error | Scoreboard | Normal | tc_fft_overflow_F3_1_9 | 1 | 1 | 2025-02-01 | 2025-03-24 | 2 | 1 | 2025-09-17 | 2025-09-19 | 2 | 2 | 2025-09-17 | 2025-09-19 | Nhannh18
Note on G5: Be careful name rule

## 7.Scenario_flow
SCENARIO FLOW
* Guideline:
- Use symbols/lines in Flowchart/Lines group in tab Insert>Shapes
Ex: |  | - Do not use backgound color in box
1. Flow of "Scenario_name" |  | - Use keyword "START/END/HALT" for terminator
Common flow chart symbols:
|  | Flowchart of FFT |  | Timing data output and status

## 8.SVA_List
SVA List
5 | Items | Check signal | Check item | Description | Property | assertion/cover/proterty name | Note
| Function | m_axis_status_tvalid | raise | Check: m_axis_status_tvalid is raised at the same time as m_axis_data_tlast | Assert | STATUS_AND_DATA_VALID_TIMING
| Interface | aresetn | raise | Check: Behavior of FFT when aresetn is asserted during operation | Cover | GLITCH_RESET_TEST
Note on D5: Author: Determine the item check such as initial value, connection, pusle, rise, fall…

## tc_reset_on_the_fly_F1_1
1. Test name
tc_reset_on_the_fly_F1_1
./testcase/reset_test/tc_reset_on_the_fly_F1_1/tc_reset_on_the_fly_F1_1.sv
2. Objective
Verify operation of DUT when trigger reset at different point and resume normal operation after reset release.
3. Scenario flow
1. Build phase
1. Enable default_tready and zero_delay_enableof Slave VIP 2. Config reset_typeof Master/Slave VIP is RESET_ALL_XACT
2. Run phase
1. Generate clock 200Mhz, assert and deassert reset.
2. Start salve sequence for data and status to generate response data.
3. Send cfg (nfft = 3 and others field is default ) and randomly input data (called normal transfer)
4. Check output result with model.
Enable cover property for GLITCH_RESET_TEST
5. Send normal transfer and wait 4 cycles (streaming input)
6. Trigger asynchronous reset for 20 cycles then release reset.
7. Stop 4 sequencer (cfg, input data, output data, status)
8. Start salve sequence for data and status to generate response data.
9. Send normal transfer and check output result with model.
10. Send normal transfer and wait 12 cycles (calculating data)
11. Trigger asynchronous reset for 60 cycles then release reset.
12. Stop 4 sequencer (cfg, input data, output data, status)
13. Start salve sequence for data and status to generate response data.
14. Send normal transfer and check output result with model.
15. Send normal transfer and wait 35 cycles (streaming data out with last beat)
16. Trigger asynchronous reset for 100 cycles then release reset.
17. Stop 4 sequencer (cfg, input data, output data, status)
18. Start salve sequence for data and status to generate response data.
19. Send normal transfer and check output result with model.
20. Repeat from step 5 to step 19, but trigger a one-cycle reset pulse.
21. End test
4. Result
GLITCH_RESET_TEST: Cover properties are used to verify that the expected stimulus sequences occur during simulation.

## tc_fft_no_default_tready_F2_1
1. Test name
tc_fft_no_default_tready_F2_1
./testcase/reset_test/tc_fft_no_default_tready_F2_1/tc_fft_no_default_tready_F2_1.sv
2. Objective
Verify operation of the DUT when disable default_tready
3. Scenario flow
1. Build phase
1. Disable default_tready and zero_delay_enableof Slave VIP
2. Run phase
1. Generate clock 200Mhz, assert and deassert reset.
2. Start salve sequence for data and status to generate response data.
3. Send cfg (random all field ) and randomly input data (called normal transfer)
4. Check output result with model.
5. Repeat 1000 times step 3-4
6. End test
4. Result

## 9.Q&A
Q&A
No | Date | Status | Questioner | Question | Answer | Responden by | Attached File | Remark
1 |  | Open
2 |  | Close
3 |  | Suspend
4 |  | Open
5 |  | Open
6 |  | Open
7 |  | Open
8 |  | Open
9 |  | Open
10 |  | Open
11 |  | Open